CompTIA

Project+

Comprehensive Exam Study Guide

Exam Code: PK0-005

75 Questions  •  90 Minutes  •  Passing Score: 710 / 900

# Exam Overview

| Exam Detail | Information |
| --- | --- |
| Exam Code | PK0-005 |
| Number of Questions | Up to 75 |
| Question Types | Multiple choice, performance-based |
| Time Limit | 90 minutes |
| Passing Score | 710 (on a scale of 100–900) |
| Recommended Experience | 6–12 months project management experience |
| Languages | English, Japanese |
| Price (USD) | $358 |

## Domain Weighting

| Domain | % of Exam |
| --- | --- |
| 1. Project Management Concepts | 33% |
| 2. Project Life Cycle Phases | 30% |
| 3. Tools, Documentation & Artifacts | 17% |
| 4. Basics of IT and Governance | 20% |

| 📌 TIP | Focus your deepest study effort on Domains 1 and 2 — they account for 63% of the exam. |
| --- | --- |

# Domain 1: Project Management Concepts (33%)

## 1.1 Project Characteristics

A project is a temporary endeavor undertaken to create a unique product, service, or result.

Key Project Characteristics

• Temporary – has a definite start and end date

• Unique – produces a distinct deliverable

• Progressive elaboration – detail is developed incrementally

• Resources – requires people, money, equipment, etc.

• Purpose – driven by a business need or strategic goal

| Project vs. Operations | Description |
| --- | --- |
| Project | Temporary, unique, has a defined end |
| Operations | Ongoing, repetitive, no defined end |
| Program | Group of related projects managed together |
| Portfolio | Collection of programs/projects aligned to strategy |

## 1.2 Project Management Process Groups

| Process Group | Key Activities |
| --- | --- |
| Initiating | Define scope, identify stakeholders, develop project charter |
| Planning | Create WBS, schedule, budget, risk plan, communication plan |
| Executing | Direct & manage work, acquire resources, manage quality |
| Monitoring & Controlling | Track progress, manage changes, control scope/cost/schedule |
| Closing | Obtain acceptance, archive documents, release resources, lessons learned |

| ⚠️ EXAM | These are NOT phases — multiple process groups overlap during a project. Monitoring & Controlling occurs throughout all phases. |
| --- | --- |

## 1.3 Project Constraints (The Triple Constraint)

Every project is constrained by Scope, Schedule (Time), and Cost. Quality is often added as a fourth constraint. A change in one affects the others.

Six Constraints to Know

• Scope – the work to be done

• Schedule – the timeline

• Cost – the budget

• Quality – meeting requirements/standards

• Resources – people, equipment, materials

• Risk – uncertainty that could affect objectives

## 1.4 Organizational Structures

| Structure | PM Authority | Key Feature |
| --- | --- | --- |
| Functional | Little/None | PM is a coordinator; functional managers hold power |
| Weak Matrix | Limited | PM has some authority; functional managers dominant |
| Balanced Matrix | Equal | Shared authority between PM and functional manager |
| Strong Matrix | High | PM has more authority than functional manager |
| Projectized | Full | PM has complete authority; team dedicated to project |

## 1.5 Project Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Sponsor | Champions the project, approves charter, provides funding |
| Project Manager | Plans, executes, monitors, controls, closes the project |
| Project Team | Executes the work; subject matter experts |
| Stakeholder | Anyone affected by or who affects the project |
| Functional Manager | Manages resources in functional departments |
| Customer | Receives the product/service/result of the project |
| Vendor/Supplier | Provides external goods or services |
| Steering Committee | Provides governance and high-level direction |

## 1.6 Leadership & Team Management

### Leadership Styles

| Style | Description |
| --- | --- |
| Autocratic / Directing | PM makes all decisions; good for crises |
| Consultative / Delegating | PM gathers input but decides; team has authority |
| Democratic / Participative | Team makes decisions collaboratively |
| Laissez-faire | Team self-directs with minimal PM involvement |
| Servant Leadership | PM removes obstacles and serves the team's needs |
| Transformational | Inspires and motivates through vision |
| Transactional | Motivates through rewards and penalties |

### Tuckman's Team Development Stages

| Stage | Characteristics |
| --- | --- |
| Forming | Team meets; polite, roles unclear, low productivity |
| Storming | Conflict arises; competition for roles/ideas |
| Norming | Consensus builds; team establishes processes |
| Performing | High productivity; team is cohesive and effective |
| Adjourning | Project ends; team disbands |

## 1.7 Communication

Communication is one of the most critical PM skills. The formula for communication channels is:

N × (N - 1) / 2   where N = number of stakeholders

Example: 5 stakeholders = 5×4/2 = 10 channels

Communication Methods

• Interactive – real-time, two-way (meetings, phone calls, video conferences)

• Push – sent to recipient; no confirmation of understanding (email, memos, reports)

• Pull – recipient retrieves information (intranet, knowledge base, document repositories)

## 1.8 Motivation Theories

| Theory | Key Concept |
| --- | --- |
| Maslow's Hierarchy of Needs | Physiological → Safety → Social → Esteem → Self-Actualization |
| Herzberg's Two-Factor Theory | Hygiene factors prevent dissatisfaction; motivators create satisfaction |
| McGregor Theory X | Workers are lazy; need to be controlled and directed |
| McGregor Theory Y | Workers are self-motivated and seek responsibility |
| McClelland's Achievement Theory | Motivated by Achievement, Affiliation, or Power |
| Expectancy Theory (Vroom) | Motivation = Expectancy × Instrumentality × Valence |

# Domain 2: Project Life Cycle Phases (30%)

## 2.1 Initiating Phase

The initiating phase authorizes the project and defines its high-level scope.

Key Initiating Outputs

• Project Charter – formally authorizes the project; issued by the sponsor

• Stakeholder Register – identifies all stakeholders and their interests/influence

• Business Case – justifies the project with cost-benefit analysis

• Statement of Work (SOW) – describes the products, services, or results to be supplied

• Project Kick-off Meeting – introduces the team and aligns expectations

### Project Charter Contents

• Project title and description

• Business need / problem statement

• High-level scope and deliverables

• High-level schedule and budget

• Project sponsor name and signature

• Project manager name and authority level

• High-level risks and assumptions

## 2.2 Planning Phase

The most detailed phase. Planning documents guide execution and form the Performance Measurement Baseline (PMB).

| Planning Document | Purpose |
| --- | --- |
| Project Management Plan | Master plan integrating all subsidiary plans |
| Scope Management Plan | How scope will be defined, validated, and controlled |
| Requirements Management Plan | How requirements will be collected and managed |
| Schedule Management Plan | How schedule will be developed and controlled |
| Cost Management Plan | How costs will be estimated, budgeted, and controlled |
| Quality Management Plan | How quality requirements will be met |
| Resource Management Plan | How resources will be planned and managed |
| Communication Management Plan | Who needs what information, when, and how |
| Risk Management Plan | How risks will be identified, analyzed, and responded to |
| Procurement Management Plan | How procurement will be planned and managed |
| Stakeholder Engagement Plan | How stakeholder engagement will be managed |

## 2.3 Scope Management

### Work Breakdown Structure (WBS)

A hierarchical decomposition of the total scope of work. The lowest level is called a Work Package.

WBS Key Terms

• Work Package – smallest unit; can be scheduled, cost-estimated, and assigned

• WBS Dictionary – describes each component in detail

• Control Account – management point where scope, schedule, and cost are integrated

• 100% Rule – WBS must include 100% of the project scope; nothing more, nothing less

| ⚠️ EXAM | The WBS captures WHAT needs to be done, not HOW (that's in the schedule). Never include activities in a WBS — only deliverables. |
| --- | --- |

### Scope Creep vs. Gold Plating

| Term | Definition |
| --- | --- |
| Scope Creep | Uncontrolled addition of features without approval through change control |
| Gold Plating | Team adds features beyond scope without customer request (also bad) |

## 2.4 Schedule Management

### Scheduling Techniques

| Technique | Description |
| --- | --- |
| Critical Path Method (CPM) | Longest path through the network; zero float = critical |
| Program Evaluation Review Technique (PERT) | Weighted average using Optimistic, Most Likely, Pessimistic |
| Gantt Chart | Bar chart showing tasks over time; easy to understand |
| Resource Leveling | Adjusts schedule to resolve resource conflicts; may extend timeline |
| Fast Tracking | Perform tasks in parallel; increases risk |
| Crashing | Add resources to critical path tasks; increases cost |
| Schedule Compression | Reduce schedule without reducing scope (fast track or crash) |

### PERT Formula

PERT = (O + 4M + P) / 6

O = Optimistic, M = Most Likely, P = Pessimistic

### Float / Slack

| Type | Definition |
| --- | --- |
| Total Float | Amount a task can be delayed without delaying project end date |
| Free Float | Amount a task can be delayed without delaying the NEXT task |
| Critical Path | Sequence of tasks with zero total float; longest duration path |

## 2.5 Cost Management

| Term | Definition |
| --- | --- |
| Analogous Estimating | Expert judgment based on similar past projects (least accurate) |
| Parametric Estimating | Statistical model (e.g., cost per sq ft); moderate accuracy |
| Bottom-up Estimating | Sum of all work packages; most accurate but time-consuming |
| Three-Point Estimating | Uses O, M, P values — same as PERT |
| Contingency Reserve | Budget for known-unknown risks (within baseline) |
| Management Reserve | Budget for unknown-unknown risks (outside baseline) |
| Cost Baseline | Approved, time-phased budget excluding management reserve |

### Earned Value Management (EVM)

| Acronym | Term | Formula / Meaning |
| --- | --- | --- |
| PV | Planned Value | Budgeted cost of work scheduled (baseline) |
| EV | Earned Value | Budgeted cost of work performed |
| AC | Actual Cost | Actual cost of work performed |
| BAC | Budget at Completion | Total approved budget |
| CV | Cost Variance | EV − AC (negative = over budget) |
| SV | Schedule Variance | EV − PV (negative = behind schedule) |
| CPI | Cost Performance Index | EV / AC (<1 = over budget) |
| SPI | Schedule Performance Index | EV / PV (<1 = behind schedule) |
| EAC | Estimate at Completion | BAC / CPI (if current rate continues) |
| ETC | Estimate to Complete | EAC − AC |
| VAC | Variance at Completion | BAC − EAC |

## 2.6 Risk Management

### Risk Management Process

| Step | Description |
| --- | --- |
| 1. Plan Risk Management | How risks will be managed |
| 2. Identify Risks | Risk register; brainstorm, checklists, interviews |
| 3. Qualitative Analysis | Probability × Impact matrix to prioritize |
| 4. Quantitative Analysis | Numerical analysis (Monte Carlo, decision trees) |
| 5. Plan Risk Responses | Strategies: Avoid, Transfer, Mitigate, Accept |
| 6. Implement Responses | Execute the response plans |
| 7. Monitor Risks | Track known risks; identify new risks |

### Risk Response Strategies

| Strategy | Applies To | Description |
| --- | --- | --- |
| Avoid | Threats | Eliminate the risk entirely (change plan) |
| Transfer | Threats | Shift impact to third party (insurance, contracts) |
| Mitigate | Threats | Reduce probability or impact |
| Accept | Threats | Acknowledge risk; no action (active or passive) |
| Exploit | Opportunities | Ensure the opportunity occurs |
| Share | Opportunities | Partner to capture the benefit |
| Enhance | Opportunities | Increase probability or positive impact |
| Accept | Opportunities | Take advantage if it occurs |

| 📌 TIP | Risk = Threat (negative) OR Opportunity (positive). Residual risk is remaining after response; secondary risk is created BY the response. |
| --- | --- |

## 2.7 Executing Phase

Key Executing Activities

• Direct and manage project work

• Manage quality assurance

• Acquire, develop, and manage project team

• Manage communications

• Implement risk responses

• Conduct procurements

## 2.8 Monitoring & Controlling Phase

Key M&C Activities

• Integrated change control – evaluate, approve, or reject change requests

• Validate scope – formal acceptance of deliverables by customer

• Control scope, schedule, cost, quality

• Monitor risks and communications

• Control procurements

| ⚠️ EXAM | Validate Scope = customer acceptance. Control Quality = internal quality checks. Validate Scope happens AFTER Control Quality. |
| --- | --- |

## 2.9 Closing Phase

Key Closing Activities

• Obtain formal project acceptance from sponsor/customer

• Release project resources

• Close contracts and procurements

• Document lessons learned

• Archive project records

• Celebrate team success

• Transition deliverable to operations

# Domain 3: Tools, Documentation & Artifacts (17%)

## 3.1 Key Project Documents

| Document | Purpose & When Used |
| --- | --- |
| Project Charter | Authorizes the project (Initiating) |
| Project Management Plan | Master planning document (Planning) |
| Stakeholder Register | Lists all stakeholders (Initiating/Planning) |
| Requirements Documentation | Documents stakeholder requirements (Planning) |
| WBS & WBS Dictionary | Decomposes project scope (Planning) |
| Project Schedule | Timeline with tasks, durations, dependencies (Planning) |
| Risk Register | Log of identified risks and responses (Planning+) |
| Issue Log | Tracks problems that have occurred (Executing) |
| Change Log | Tracks all change requests (M&C) |
| Lessons Learned | Documents what went well and what didn't (Closing) |
| Project Status Report | Regular communication of progress (M&C) |

## 3.2 Common Project Management Tools

| Tool | Use Case |
| --- | --- |
| Gantt Chart | Schedule visualization; task timelines and dependencies |
| Network Diagram (PDM) | Show task dependencies; calculate critical path |
| RACI Matrix | Roles: Responsible, Accountable, Consulted, Informed |
| SWOT Analysis | Strengths, Weaknesses, Opportunities, Threats |
| Fishbone / Ishikawa Diagram | Root cause analysis |
| Histogram | Show frequency distribution (resource use, defects) |
| Pareto Chart | 80/20 rule; rank defects from most to least frequent |
| Control Chart | Monitor process performance; identify special cause variation |
| Scatter Diagram | Show correlation between two variables |
| Decision Tree | Quantitative risk analysis; EMV calculation |
| Monte Carlo Simulation | Quantitative risk; runs thousands of scenarios |

## 3.3 Contract Types

| Contract Type | Who Bears Risk | Description |
| --- | --- | --- |
| Fixed Price (FFP) | Seller | Set price; seller absorbs cost overruns |
| Fixed Price Incentive Fee (FPIF) | Shared | Fixed price + incentive for beating targets |
| Cost Plus Fixed Fee (CPFF) | Buyer | Reimburse costs + fixed fee |
| Cost Plus Incentive Fee (CPIF) | Buyer+ | Reimburse costs + incentive fee |
| Time & Materials (T&M) | Buyer | Pay per hour + materials; no defined end |

| 📌 TIP | Fixed price is BEST when scope is well-defined. T&M is riskiest for the buyer because costs are open-ended. CPFF is safest for the seller. |
| --- | --- |

## 3.4 Change Management

Integrated Change Control Process

• 1. Change request submitted (by anyone)

• 2. Change Control Board (CCB) reviews the request

• 3. Impact analysis performed (scope, schedule, cost, quality, risk)

• 4. CCB approves, rejects, or defers

• 5. Project plans updated (if approved)

• 6. Change log updated

• 7. Stakeholders notified

| ⚠️ EXAM | No change is implemented without formal approval. Even verbal approvals must be documented. The PM cannot approve changes unilaterally. |
| --- | --- |

## 3.5 Quality Tools

| Concept | Definition |
| --- | --- |
| Quality Assurance (QA) | Process audits to ensure correct processes are being followed |
| Quality Control (QC) | Inspect deliverables for defects; product-focused |
| Prevention vs. Inspection | Prevention (design out errors) costs less than inspection (find errors) |
| Cost of Quality (CoQ) | Conformance costs + Non-conformance costs |
| Control Limits | Statistical limits (±3σ); points outside = investigate |
| Specification Limits | Customer requirements; tighter than control limits usually |

# Domain 4: Basics of IT and Governance (20%)

## 4.1 IT Project Governance

Governance provides the framework for decision-making, accountability, and control of IT projects.

Governance Components

• Policies – rules that guide decisions and behavior

• Procedures – step-by-step instructions implementing policies

• Standards – required methods or specifications

• Guidelines – recommended (not mandatory) best practices

• PMO (Project Management Office) – sets standards, provides governance, supports PMs

### PMO Types

| PMO Type | Role |
| --- | --- |
| Supportive | Provides templates, training, information; low control |
| Controlling | Requires compliance with methodology; moderate control |
| Directive | Manages projects directly; high control |

## 4.2 Regulatory & Compliance Considerations

| Area | Examples |
| --- | --- |
| Data Privacy | GDPR, HIPAA, CCPA — protecting personal data |
| Security Compliance | SOX, PCI-DSS — financial and payment standards |
| Environmental | EPA regulations, green IT requirements |
| Industry-Specific | FDA for healthcare, FAA for aviation |
| Intellectual Property | Patents, copyrights, licensing agreements |

## 4.3 IT Infrastructure Concepts

| Concept | Description |
| --- | --- |
| Cloud Computing | On-demand IT resources over the internet (IaaS, PaaS, SaaS) |
| Virtualization | Running multiple virtual machines on one physical host |
| Network | LAN, WAN, VPN — infrastructure connecting systems |
| Security | CIA triad: Confidentiality, Integrity, Availability |
| SDLC | Software Development Life Cycle — process for building software |
| DevOps | Combining development and operations for continuous delivery |
| Agile | Iterative development; value delivery in sprints/iterations |

## 4.4 Project Methodologies

| Methodology | Description & Best For |
| --- | --- |
| Waterfall / Predictive | Sequential phases; best for stable, well-defined scope |
| Agile | Iterative, flexible; best for changing requirements |
| Scrum | Agile framework; sprints, backlog, daily standups, retrospectives |
| Kanban | Visual workflow management; continuous flow |
| Hybrid | Combines predictive and agile elements |
| PRINCE2 | UK government standard; focus on business justification |
| PMBOK | PMI's guide of best practices; not prescriptive methodology |

### Scrum Key Roles & Events

| Item | Description |
| --- | --- |
| Product Owner | Owns the product backlog; prioritizes features |
| Scrum Master | Facilitates scrum; removes impediments (NOT a PM) |
| Development Team | Self-organizing team delivering the sprint increment |
| Sprint | Time-boxed iteration (typically 1–4 weeks) |
| Sprint Planning | Team selects items from backlog to complete in sprint |
| Daily Scrum | 15-minute standup: What I did, What I'll do, Blockers |
| Sprint Review | Demonstrate completed work to stakeholders |
| Sprint Retrospective | Reflect on process improvements |

## 4.5 Vendor & Procurement Management

Procurement Process Steps

• 1. Plan Procurement Management – decide what to buy

• 2. Conduct Procurements – solicit bids (RFP, RFQ, IFB), select vendor

• 3. Control Procurements – manage contract performance

• 4. Close Procurements – verify all work done, close contract

| Solicitation Document | Description |
| --- | --- |
| RFI (Request for Information) | Gather market info; no commitment to purchase |
| RFQ (Request for Quotation) | Ask for price quote; used for commodity items |
| RFP (Request for Proposal) | Detailed proposal request; for complex needs |
| IFB (Invitation for Bid) | Formal sealed bid; lowest qualifying bid wins |

# Key Terms Glossary

| Term | Definition |
| --- | --- |
| Assumption | Factor considered to be true for planning purposes |
| Baseline | Approved version of a plan (scope, schedule, cost) |
| Benchmarking | Comparing practices/results to industry standards |
| Constraint | Limiting factor affecting project execution |
| Deliverable | Measurable, tangible output of a project |
| Dependencies | Logical relationships between activities (FS, SS, FF, SF) |
| Float/Slack | Time an activity can be delayed without delaying the project |
| Issue | A risk that has occurred |
| Kickoff Meeting | First meeting where team is introduced and goals aligned |
| Lessons Learned | Knowledge gained during project for future reference |
| Milestone | Significant point or event in a project; zero duration |
| Predecessor | Task that must finish/start before successor can begin |
| Risk Appetite | Degree of uncertainty an organization is willing to accept |
| Risk Tolerance | The threshold an entity is ready to accept before action |
| Scope Creep | Uncontrolled expansion of scope without proper approval |
| Sponsor | Person who champions and funds the project |
| Stakeholder | Individual or group affected by or affecting the project |
| Successor | Task that depends on a predecessor task |
| Threshold | A point at which a stakeholder will take notice or action |
| Trigger | Indicator that a risk event may occur (risk symptom) |

# Exam Strategy & Study Tips

## Test-Taking Strategies

On Exam Day

• Read each question completely before looking at answers

• Eliminate obviously wrong answers first

• Look for absolute words ('always', 'never') — these are often wrong

• Choose the BEST answer, not just a correct one

• Trust process-based answers over individual judgment

• When in doubt, follow the PMI process (plan before doing, communicate often)

• Flag uncertain questions and review at the end

• Don't change answers without good reason

## Common Exam Traps

| Trap | What to Do Instead |
| --- | --- |
| 'What should the PM do first?' | Usually: assess/analyze, then communicate, then act |
| Conflict resolution question | Collaborating/Problem-solving is almost always the best answer |
| Scope change requested | Document it → submit to CCB → wait for approval |
| Team conflict | Address it early, directly, and collaboratively |
| Quality issue found | Always fix root cause, not just symptoms |
| Sponsor pressure to skip steps | Follow the process; document everything |

## Priority Study Checklist

Must-Know for the Exam

• ✅ Five process groups and their order

• ✅ Triple constraint and how changes affect each element

• ✅ Critical Path Method and float calculation

• ✅ EVM formulas: CV, SV, CPI, SPI, EAC

• ✅ Risk response strategies (threats vs. opportunities)

• ✅ WBS 100% rule and work packages

• ✅ RACI matrix roles

• ✅ Contract types and who bears risk

• ✅ Tuckman's team stages

• ✅ Communication channels formula: N(N-1)/2

• ✅ Validate Scope vs. Control Quality difference

• ✅ Change control process steps

• ✅ Organizational structure types and PM authority

## Recommended Study Plan (4 Weeks)

| Week | Focus Area |
| --- | --- |
| Week 1 | Domain 1: PM Concepts – process groups, constraints, org structures, roles |
| Week 2 | Domain 2 (Part 1): Initiating, Planning – scope, WBS, schedule, CPM, EVM |
| Week 3 | Domain 2 (Part 2) + Domain 3: Risk, quality, contracts, tools, change control |
| Week 4 | Domain 4 + Review: IT governance, methodologies, practice exams, weak areas |

| 📌 FINAL TIP | Take at least 2 full practice exams under timed conditions before test day. Review every wrong answer to understand the reasoning, not just the correct answer. |
| --- | --- |